		YOUR LOGO



Your Company Name
Trading name  ·  Tax ID  ·  Licence no. (if required)
Address  ·  Phone  ·  Email
	COST PLUS

	Invoice no.
	INV-1047

	Date
	3 Aug 2026

	Payment due
	Net 14

	Contract / PO
	HC-0000

	Period
	1–31 July 2026






	BILL TO



	Client
	Harding Constructions
	
	Attention
	

	Billing address
	
	
	Project
	Willow St Townhouses — Lot 4

	Site address
	22 Willow St
	
	Contract / PO
	HC-2261



	LINE ITEMS


	Cost description
	Unit price
	Qty
	Total

	Structural pine 90x45
	$8.40
	120.00
	$1,008.00

	Roof underlayment roll
	$145.00
	6.00
	$870.00

	Carpenter — framing
	$68.00
	42.00
	$2,856.00

	Scaffold hire (weekly)
	$320.00
	2.00
	$640.00



		PAYMENT



	Bank / account
	

	Accepted methods
	

	Late payment terms
	



	
		Cost total
	$5,374.00

	Plus agreed margin (12%)
	$644.88

	Subtotal
	$6,018.88

	Tax (10%)
	$601.89






	AMOUNT DUE THIS INVOICE
	$6,620.77



	CONTRACTOR SIGNATURE  ·  DATE
	
	CLIENT / SUPERINTENDENT SIGNATURE  ·  DATE




DISCLAIMER

This template is provided for general reference only. Invosmith does not provide accounting, tax or legal advice, and nothing in this document is a substitute for advice from your own qualified adviser.
Requirements for contractor licence numbers, sales tax, GST or VAT treatment, retainage limits and statutory progress-payment rights vary by country, state and contract. Confirm what applies to your work and to the contract you are billing under before you issue an invoice.
The figures shown in the completed example are illustrative and do not represent typical or recommended amounts.
This page is not part of the invoice. Print or send page 1 only.
Template by Invosmith  ·  invosmith.com
