| YOUR LOGO. Your Company Name Trading name · Tax ID · Licence no. (if required) Address · Phone · Email | PROGRESS CLAIM Invoice no.; INV-1047. Date; 3 Aug 2026. Payment due; Net 14. Contract / PO; HC-0000. Claim No.; 3. Claim period; 1–31 July 2026. |
| --- | --- |

BILL TO

| Client | Harding Constructions |  | Attention |  |
| --- | --- | --- | --- | --- |
| Billing address |  |  | Project | Willow St Townhouses — Lot 4 |
| Site address | 22 Willow St |  | Contract / PO | HC-2261 |

LINE ITEMS

| Description of work | Contract value | % complete | Completed to date |
| --- | --- | --- | --- |
| Site preparation | $6,000.00 | 100% | $6,000.00 |
| Wall framing | $34,000.00 | 100% | $34,000.00 |
| Roof framing | $18,000.00 | 85% | $15,300.00 |
| Blocking & bracing | $7,000.00 | 0% | $0.00 |

APPROVED VARIATIONS / CHANGE ORDERS

| Ref | Description | Amount |
| --- | --- | --- |
| CO-02 | Additional bracing, north wall (approved 18 Jul) | $2,400.00 |

| RETAINAGE HELD TO DATE. Previously held; $3,800.00. Held this claim; $1,970.00. Total retainage held; $5,770.00. Released in accordance with the contract. PAYMENT. Bank / account. Accepted methods. Late payment terms. |  | Work completed to date; $55,300.00. Plus approved variations; $2,400.00. Total incl. variations; $57,700.00. Less previously claimed; ($38,000.00). CURRENT CLAIM; $19,700.00. Tax (10%); $1,970.00. Subtotal; $21,670.00. Less retainage this claim (10%); ($1,970.00). |
| --- | --- | --- |

| AMOUNT DUE THIS INVOICE | $19,700.00 |
| --- | --- |

| CONTRACTOR SIGNATURE · DATE |  | CLIENT / SUPERINTENDENT SIGNATURE · DATE |
| --- | --- | --- |

DISCLAIMER

This template is provided for general reference only. Invosmith does not provide accounting, tax or legal advice, and nothing in this document is a substitute for advice from your own qualified adviser.

Requirements for contractor licence numbers, sales tax, GST or VAT treatment, retainage limits and statutory progress-payment rights vary by country, state and contract. Confirm what applies to your work and to the contract you are billing under before you issue an invoice.

The figures shown in the completed example are illustrative and do not represent typical or recommended amounts.

This page is not part of the invoice. Print or send page 1 only.

Template by Invosmith  ·  invosmith.com